Directions for Final Project and Presentation:

1. Develop your own project include the following;
   1. Minimum budget: $5,000
   2. Duration: Project span a minimum of 30 days
   3. Project charter
   4. Project scope
   5. Statement of work (SOW)
   6. Work breakdown structure (WBS)
      1. Create 4 WBS(s)(minimum) with 1 sibling under each WBS
      2. Include 7 (minimum) activities under each sibling
      3. Set up columns at a minimum to show the following Activity ID, Activity Name, Activity Duration, Total Float, Predecessor Details, Successor Details.
      4. Tie all activities with only two open ends (Start and Finish) Constrain your Start milestone and constrain your Finish Milestone out a minimum of 30Days
      5. Move the data date to Monday 06May19
      6. Make a PDF of the entire schedule and another one to show your Critical Path…this means you will have to filter for ALL on one and filter for Critical activities for the another one.
   7. Risk matrix
      1. What do you foresee as pitfalls?
   8. Project sign off sheet
   9. Have everything together in a single project book
   10. Written work: at least 15 pages
2. Project presentation:
   1. Duration: No more than 10 minutes
   2. Must include: PDF of the schedule (P6) showing critical path